## 2025-Q4
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION V - BICOL REGION |  | CALENDAR YEAR: | 2025
PROVINCE: | SORSOGON |  | QUARTER: | 4
CITY/MUNICIPALITY: | SANTA MAGDALENA
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Purchase and Installation of CCTV's |  | 500000 |  |  |  | 0
Rehab/Construction of Street Lights |  | 1000000 |  |  |  | 894668.81
Improvement of LGU Building | Barangay 3, Poblacion | 500000 |  |  |  | 335535
Installation of House/Building Number Plates | Poblacion 1,2,3, & 4 | 200000 |  |  |  | 0
Economic Development
MDFO (Loan Amortization) |  | 3000000 |  |  |  | 2927329.5
Livelihood Program (SAGIPSAKA,) |  | 1400000 |  |  |  | 1330800
Rehabilitation of Irrigation Canals | San Isidro/Matacla,San Eugenio | 2500000 |  |  |  | 0
Construction of Slope Protection |  | 698061.54 |  |  |  | 698061.54
Construction of Bridge (Poblacion 4) | San Roque | 300000 |  |  |  | 208982.92
Rehabilitation of LGU Water System (Peñafrancia) | Peñafrancia | 300000 |  |  |  | 227239
Construction of Boulevard/Seaside Promenade | Poblacion 3 | 4180158.94 | 2025-03-27 |  |  | 4180158.94
Masterplan of Poblacion Drainage System | Poblacion 1, 2, 3 & 4 | 1000000 |  |  |  | 0
Construction of Pathway |  | 2700000 |  |  |  | 1880846.31
Construction of Mun. Dog Impounding Facility |  | 100000
Improvement of Slaughter House |  | 2585852.23
Environmental Management
Rehabilitation of Seawall | Portion of Poblacion 1 & Poblacion 4 | 2000000 |  |  |  | 0
Construction of Flood Control | Poblacion 4 | 3000000 |  |  |  | 0
TOTAL |  | 25964072.71 |  |  |  | 12683622.02
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| ANITA B. CORREA |  |  |  | HON. MARK JEWERY G. LOZANO
| Local Budget Officer |  |  |  | Local Chief Executive