## Sheet1
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
PROVINCE: | SORSOGON |  |  |  |  | CALENDAR YEAR: | 2026
CITY/MUNICIPALITY: | SANTA MAGDALENA |  |  |  |  | QUARTER: | 1ST
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Pension for Senior Citizens for C.Y. 2025 | Sta. Magdalena, Sorsogon | 4941000 | 2026-03-19 |  | 0% | 0 |  | On Going
Completion/Upgrading/ Repair Of Sta. Magdalena Super Health | Barangay San Bartolome, Sta. Magdalena, Sorsogon | 4900000 | 2025-12-08 | 2026-04-08 | 14.98% | 734243.35 |  | On-going implementation with 80% accomplishment requested time extension due to weather disturbance on December, January and February.
DILG - GEF | Sta. Magdalena, Sorsogon | 30000000 | 2026-03-18 |  | 0% | 0 |  | On Going
DILG - Nutrition | Sta. Magdalena, Sorsogon | 2780000 | 2026-03-18 |  | 0% | 0 |  | On Going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ANITA B. CORREA (SGD) |  |  | ROMMEL F. GRUBA (SGD) |  |  | MARK JEWERY G. LOZANO (SGD)
Local Budget Officer |  |  | Local Accountant |  |  | Local Chief Executive